## Development Roadmap
TigerHawk TMS Development Roadmap
Target: 8-week MVP ¦ Team Size: 2 partners
Week | Phase | Task | Owner | Status | Hours Est. | Notes
Phase 1: Foundation
1-2 |  | Register for Port Houston API access | Both | Not Started | 2 | Apply at porthouston.com - 2-4 week approval
1-2 |  | Set up GitHub repository and project structure | Partner A | Not Started | 2 | Private repo, add both as collaborators
1-2 |  | Initialize Next.js app with Tailwind CSS | Partner A | Not Started | 3 | npx create-next-app@latest
1-2 |  | Set up Supabase project and authentication | Partner B | Not Started | 4 | Create project, configure auth, get API keys
1-2 |  | Create database schema in Supabase | Partner B | Not Started | 6 | All tables from tech spec
1-2 |  | Build Port Houston API integration | Partner B | Not Started | 8 | Python script for vessel sync
1-2 |  | Create vessel dashboard UI | Partner A | Not Started | 8 | Display upcoming arrivals
1-2 |  | Set up Vercel deployment | Both | Not Started | 2 | Connect GitHub, configure env vars
Phase 2: Core Operations
3-4 |  | Container tracking interface | Partner A | Not Started | 8 | Search, filter, status display
3-4 |  | Shipment creation form | Partner A | Not Started | 6 | Customer select, container link
3-4 |  | Gate appointment booking integration | Partner B | Not Started | 6 | Port Houston createAppointment API
3-4 |  | Driver management CRUD | Partner A | Not Started | 4 | Add/edit/delete drivers
3-4 |  | Job assignment workflow | Partner A | Not Started | 8 | Drag-drop or select driver
3-4 |  | Driver mobile interface | Partner A | Not Started | 8 | Responsive views for status updates
3-4 |  | Email notification system | Partner B | Not Started | 6 | Resend integration, templates
3-4 |  | Status tracking API endpoints | Partner B | Not Started | 4 | Update shipment status
Phase 3: Warehouse & Automation
5-6 |  | Warehouse inventory module | Partner A | Not Started | 8 | CRUD for inventory items
5-6 |  | Transload tracking | Partner A | Not Started | 4 | Link inventory to shipments
5-6 |  | Document upload/storage | Partner B | Not Started | 6 | Supabase Storage integration
5-6 |  | Automated vessel arrival alerts | Partner B | Not Started | 4 | Email on new vessel sync
5-6 |  | Container availability alerts | Partner B | Not Started | 4 | Notify when container ready
5-6 |  | Detention/demurrage warnings | Partner B | Not Started | 3 | Alert before last free day
5-6 |  | Basic reporting dashboard | Partner A | Not Started | 6 | Charts for key metrics
Phase 4: Customer Portal & Billing
7-8 |  | Customer portal authentication | Partner B | Not Started | 4 | Supabase Auth, customer role
7-8 |  | Customer shipment tracking page | Partner A | Not Started | 6 | Search by reference, view status
7-8 |  | Rate management interface | Partner A | Not Started | 6 | Configure pricing rules
7-8 |  | Invoice generation | Partner B | Not Started | 8 | Calculate charges, generate PDF
7-8 |  | Financial reporting dashboard | Partner A | Not Started | 6 | Revenue, outstanding invoices
7-8 |  | User acceptance testing | Both | Not Started | 8 | Test all workflows end-to-end
7-8 |  | Bug fixes and polish | Both | Not Started | 8 | Fix issues from testing
7-8 |  | Documentation and training | Both | Not Started | 4 | User guides, video walkthrough
7-8 |  | Go-live preparation | Both | Not Started | 4 | Final checks, parallel run with PortPro
SUMMARY
Total Tasks: |  |  | Partner A Tasks:
Total Hours: |  |  | Partner B Tasks:
Both Tasks:
INSTRUCTIONS:
1. Update Status column as you complete tasks: Not Started → In Progress → Completed → Blocked
2. Add notes about decisions, blockers, or changes in the Notes column
3. Adjust Owner assignments based on actual workload and skills
4. Track actual hours in a new column if you want to compare estimates
5. Color codes: Green = Partner A, Orange = Partner B, Yellow = Both