# Initial analysis of the TigerHawk TMS project

Document: initial_analysis_of_the_tigerhawk_project. April 06 2026

Scope: brief summary of documented technical debt, console warnings observed, and next steps.

# 1. Executive summary

Core modules (dispatch, pay, Port Houston, portions of financials and reporting) are operational, but the product is still in an active stabilization phase: residual defects are likely despite manual testing, and the absence of automated tests and CI/CD materially increases the risk of undetected regressions. The billing and Accounts Receivable / invoicing area is not fully complete; it has been assessed by the lead developer as more complex than originally expected and should be treated as high-effort, high-schedule-risk work still under development (aligned with E2E prerequisites such as batch invoice generation from charges). Settlement-side (A/P) automation gaps remain relevant for end-to-end financial closure. Overall, remaining scope—including technical debt, incomplete financial workflows, a greenfield PortPro mobile app, and possible Warehouse Management System (WMS) work—supports a timeline expectation of at least a couple of months before the platform is robust enough for confident production-scale use. A gradual, client-by-client migration off PortPro will demand elevated stability to avoid operational disruption.

# 2. Outstanding work by phase

## Phase 1 — Stability (mandatory)

Maps and geocoding: origins missing lat/lng; backfill and manual entry where city/state is missing.

Remove hardcoded values: e.g. terminal names in vessel/container tables; replace with database-driven data.

Dual transactions: the estimated savings field is 0; implement calculation using actual distance between points.

Fill down: after the partial fix, validate regressions and bulk-edit scenarios.

## Phase 2 — Technical quality

Set up testing (Jest + Testing Library) and Supabase mocks.

Critical tests: pay calculator and load flows (statuses, assignments).

CI/CD: pipeline (e.g. GitHub Actions) with lint, typecheck, and tests; reproducible build.

## Critical product gap — Billing / invoicing (A/R)

The A/R invoicing module is not fully complete; treat completion as a critical path item, not a polish task.

Lead developer feedback: billing logic and integration are more complex than initially expected—plan for sustained engineering effort and design iteration.

Carry elevated schedule and quality risk until batch invoicing from charges, invoice lifecycle, and related UI/API flows are implemented, tested, and signed off.

## Phase 3 — UX and robustness

Consistent error handling and loading states (including dashboards and lists).

Full CSV exports on main views/tables.

Email flows (Resend): triggers, errors, and case coverage.

## Phase 4 — Additional capabilities

Basic realtime (Supabase) for relevant operational data.

In-app notifications (beyond existing toasts where applicable).

Broader CSV import (PortPro import for loads exists; assess other entities).

Analytics/dashboard improvements (aggregations, indicators, queries).

PortPro mobile application (greenfield): no substantial implementation to date; requires full build—authentication, driver workflows, device UX, and secure API integration with the TMS backend.

Warehouse Management System (WMS): a separate WMS may need fixes or enhancements; flag as potential scope expansion or parallel engineering load.

# 3. Detected errors and risks (technical reference)

Prior documentation (Technical Handoff): partial maps, no test framework, no CI/CD pipeline, hardcoded terminals, dual transaction at 0, fill down to monitor.

Testing plan (E2E): blocking prerequisites for full execution — invoice generation from charges (A/R) and automatic settlement generation (A/P); plus recommendations (holds on transitions, deduction limits).

Stabilization reality: the codebase is past prototype but not hardened; undiscovered bugs may surface under real load or edge workflows. Lack of automated regression coverage amplifies the chance of silent breakage after changes.

PortPro migration risk: the business transition is expected to be gradual (client-by-client). Each wave exposes production traffic to partially stabilized features; insufficient stability or incomplete billing/settlement flows could translate directly into revenue, cash collection, or operational incidents.

WMS coupling: if the WMS requires remediation, it adds concurrent workstreams and can compete for the same stabilization window—account for resourcing and prioritization.

# 4. Console warnings — Dashboard

Server console messages were observed when loading the dashboard (Next.js), with no clear evidence of core functionality breaking:

Dashboard query error (perDiem): {} — source: getDashboardData in app/dashboard/page.tsx (approx. line 212), after parallel Supabase queries.

Dashboard query error (holds): {} — same error-logging routine.

Dashboard query error (appointments): {} — same error-logging routine.

Code context: the perDiem, holds, and appointments queries (staff only: admin/dispatcher) use .from("loads") with nested selects (customers, containers, drivers). The loop logs any qr.error with console.error.

Hypothesis: the empty error object ({}) may be due to Supabase/PostgREST client serialization, RLS permissions on related tables, or appointment filters/or clauses returning a non-descriptive error. RLS restrictions by role or policies on linked tables (e.g. sensitive data or disallowed joins) are plausible, without affecting the rest of the dashboard.

Recommended action: validate in Supabase (RLS policies on loads, customers, containers, drivers) with the same user/role that reproduces the warning; rerun the query in the SQL editor or API logs; in code, log JSON.stringify of the error and PostgREST code/message if available.

# 5. Suggested next steps

1. Prioritize Phase 1 (maps, hardcoded values, dual transaction, fill down) to reduce regressions and bad data—this underpins safe PortPro migration waves.

2. In parallel: confirm the root cause of dashboard errors (RLS vs query syntax vs relationships) and fix or gracefully degrade with partial data per product policy.

3. Stand up Phase 2 (tests + CI) as soon as practical to shrink the gap between manually tested and continuously verified quality.

4. Drive billing / A/R completion explicitly: dedicated milestones, reviews with the lead developer on complexity hotspots, and acceptance criteria tied to invoice generation and downstream A/R views.

5. Unblock A/R and A/P items from the testing plan if the goal is pre-launch E2E completion; sequence work so invoicing maturity precedes aggressive client cutover.

6. Treat the PortPro mobile app as a separate greenfield initiative: discovery, architecture, and phased delivery after core web stabilization and API contracts are clear.

7. Clarify WMS ownership and severity early (triage vs full project) to avoid unplanned drain on the same stabilization timeline.

8. Plan for an extended delivery horizon (order of months) aligned with incomplete modules, mobile greenfield scope, migration pacing, and debt burn-down.

End of document.